## Sheet1
Task | Start Date | Days to Complete
Planning | 2018-10-12 | 14
Software And User Requirements Analysis | 2018-10-26 | 14
Software Test Case Studies And Analysis | 2018-11-09 | 10
Software Design | 2018-11-19 | 36
Software Unit Testing | 2018-11-19 | 2
Software Gui Design | 2018-11-21 | 3
Software Model Design | 2018-11-24 | 5
Software Gui and Model Integration | 2018-11-29 | 8
Database Design | 2018-12-07 | 3
Database and Software Integration | 2018-12-10 | 8
Software Final Tests | 2018-12-18 | 6
Demo | 2018-12-24 | 1